|  |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | OSA/A-Team | Self-Study Team | Campus Review Team | External Review Team |
| Prior academic year | •Appoint self-study team •Finalize standards & timeline •Introduce self-study team to program review process | •Introduce self-study team to program review process |  |  |
| August | •Create template for program review in Compliance Assist•Self-study orientation  | •Self-study orientation |  |  |
| September | •Identify Campus Review Team members•Proposed Campus Review Team members approved | •Start Self-Study•Identify Campus Review Team members |  |  |
| October |  | •Solicit and finalize Campus Review Team | •Solicit and finalize Campus Review Team |  |
| November |  |  |  |  |
| December | •Provide Compliance Assist Access to Campus Review Team members•Orientation/training meeting for Campus Review Team | •Orientation/training meeting for Campus Review Team | •Orientation/training meeting for Campus Review Team |  |
| January | •Identify External Review Team Members•Proposed External Review Team members approved | •Identify External Review Team Members | •Campus Review Team to review self-study |  |
| February | •Process contracts for External Review Team members | •Solicit and finalize External Review Team•Schedule dates for site visit | •Complete Campus Review Team review and report | •Solicit and finalize External Review Team•Schedule dates for site visit•Process contracts for External Review Team members |
| March | •Provide Compliance Assist Access to External Review Team members•Orient/train External Review Team•Coordinate/prepare External Review Team site visit | •Consider revisions to self-study (following review/recommendations of Campus Review Team)•Coordinate/prepare External Review Team site visit |  | •Review self-study/campus review team report |
| April | •External Review Team site visit | •External Review Team site visit | •External Review Team site visit | •External Review Team site visit |
| May |  |  |  | •Complete External Review Team report-30 days from site visit |
| By August | •Review final report •Post final review to A-Team website | •Generate response to External Review Team report•Submit External Review Team report and Self-Study Team Report to OSA•Share report with Campus & External Review Teams |  |  |